## Solar BOT
ELL 3 GW Alternative Market-Based Mechanism Process Solar RFP - Self-Assessment for Solar BOT Proposals
Bidder ID
Resource ID
Proposal ID
Assessment Criteria | RFP Guidance | Bidder Response | Bidder Comments
Resource Overview
Guaranteed Substantial Completion Date | The Guaranteed Substantial Completion Date may be as early as January 1, 2026.
Force Majeure Cap (Days) | The project schedule may be extended by force majeure via change order for up to a maximum total of 150 days.
MISO Interconnection Status | The proposed resource must have a fully executed GIA with MISO or be included in the 2020 or 2021 MISO DPP queue (or subsequent MISO DPP queues for which MISO has provided a Phase 1 DPP study result for the resource at the time of proposal submission ).
MISO Queue Number
Will the resource have NRIS or ERIS?
If the resource has NRIS, what NRIS amount has been requested from MISO (MW)?
If the resource has ERIS, does the Bidder anticipate electing for ELL to procure NITS in MISO at Bidder's cost and risk in lieu of Bidder obtaining NRIS? | While ELL’s strong preference is for resources that can qualify as Network Resources of ELL in MISO, ELL will not reject, and will evaluate, proposals submitted for resources that do not include the required NRIS or NITS.
Proposed Resource Size (MW) | Proposals must offer at least 50 MW (AC) of Capacity.
Physical Resource Location (City and Parish)
Provide Longitude and Latitude
Provide the nearest Substation
Physical Delivery Point (POI) | The proposed resource is required to interconnect directly to a transmission system within the Louisiana portion of MISO South
Technical Feasibility
Has the Bidder provided at least two years of onsite profile data? | Bidders must provide a complete hourly generation profile of the proposed resource and explain how it was derived. The profile should be based upon verifiable data, to the extent available, for a period of two (2) or more recent years using established, reliable, and accurate data measurement equipment at or near the site of the proposed resource and/or a third-party assessment study.
What is the source of the production profile data?
Design Life of the Plant (Years) | Minimum 30 years
Proposed Module Manufacturer | See Scope Book Appendix 9: Approved Manufacturers
Proposed Panel Type
PV Module Product Warranty (Years) | Minimum ten (10) years
PV Module Power Warranty (Years) | Minimum 25 years
Solar Panel Maximum Power Output Degradation in Year 1 (Percent) | 2% maximum
Solar Panel Maximum Power Output Degradation Beyond Year 1 (Percent) | No more than 0.5% on average
Proposed Inverter Manufacturer | See Scope Book Appendix 9: Approved Manufacturers
Inverter Voltage Rating (VDC) | 1,500 VDC
Inverter Product Warranty (Years) | Minimum five (5) years
Proposed Racking System Manufacturer | See Scope Book Appendix 9: Approved Manufacturers
Racking System Product Warranty for Moving Parts (Years) | Minimum five (5) years
Racking System Product Warranty for Structural Parts (Years) | Minimum ten (10) years
Site Hazard Risk
Were Flood (River, Pluvial, Storm Surge) hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Flood (River, Pluvial, Storm Surge) hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Equipment elevation in terms of FEMA Flood Maps and historical water levels
Were Windstorm Hazards Identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Windstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Fastening methods used, tightening methodology, description of wind tunnel testing, etc.
Were Wildfire Hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Wildfire hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Horizontal fire spread characteristics of the chosen panels and required setbacks for Wildfire
Were hailstorm hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were hailstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Use of tempered glass panels, safe-stow position, or other ways to mitigate the risk of hail damage.
Were lightening hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were lightening hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Lightning protection methodology for all buildings and structures (including solar array equipment)
What is the planned designed wind speed of the facility (MPH)? | ASCE 7: Risk Category III
Bidder Experience
How many utility scale solar projects (50 MW or greater) has the bidder completed?
How many solar projects of equal or greater size to the current proposed resource has the bidder completed?
Development Status
Has a detailed engineering study been performed?
Is the project cost estimate based on front-end engineering that supports at least a class 3 estimate (-20% to +30%)?
Has a detailed construction schedule (Level 1) been performed?
Is the proposal based on an EPC bid or an internal analysis?
Is Bidder (or proposed contractor) a licensed contractor, authorized to install solar equipment within the State of Louisiana?
Confirm the generation resource is located at a single facility and is not a combined or aggregate resource formed by a "system" of generation resources. | Eligible Resource are generation resources that are single resources are not and will not be part of a shared facility-type structure or arrangement
Confirm the selection of the proposed resource is not contingent on selection of another proposed resource. | Eligible Resource are single resources
Commercial
Confirm that Bidder has reviewed and is familiar with the terms of the RFP, including the Model BOT Agreement and Scope Book.
Has a redline of the Model BOT, Redline of the Scope Book, and the Special Exceptions tab been completed and provided?
Is the Bidder electing to self-build all stand-alone network upgrades (SANU), Transmission Owner's Interconnection Facilities (TOIF), and Interconnection Customer Interconnection Facilities (ICIF)? | The TET is responsible for assessing the interconnection, deliverability, and transmission costs and risks associated with proposals received in this RFP
What is the cost estimate included in the Purchase Price for all SANU, TOIF, and ICIF? | The TET responsibilities will include developing and providing to the RFP Administration Team cost estimates associated with interconnection, deliverability, or transmission upgrades not identified in a Bidder’s proposal or appropriately identified in the proposal but misestimated.
Confirm that the Bidder will bear all risk associated with construction and arrangement for all transmission interconnection and network upgrades associated with the Facility being fully deliverable to MISO. | All proposals must provide or accept that Bidder is responsible for all costs to obtain the interconnection, deliverability, and transmission service associated with the proposal, including, without limitation, costs associated with transmission interconnection and any network upgrades for the resource.
Provide a date, which must be at or prior to the proposed Guaranteed Substantial Completion Date, by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Guaranteed Substantial Completion Date.
Confirm the Bidder/ Seller understands that ELL as the Buyer will have the right to assign its rights and obligations under the BOT agreement to an Affiliate of Buyer. | Buyer will have the right to assign its rights and obligations under the BOT agreement to an Affiliate of Buyer
Federal Tax Credits
Provide the level of federal tax credits (in terms of ITC or PTC) that the project may qualify. | Each Bidder of a solar BOT project is required to provide a guaranteed ITC percentage for the project property
Confirm that the project would comply with the prevailing wage and apprenticeship requirements as provided under the IRA
Confirm whether the project is anticipated to be located within an "energy community" and qualify for a higher level of the federal tax credit
Confirm whether the project is anticipated to satisfy the "domestic content" requirement and qualify for a higher level of the federal tax credits; and if so, whether the elective safe harbor as provided under the IRS Notice 2024-41 would be satisfied.
Please provide the year that the Facility started or will start construction for tax credit purposes
Site Assessment
Is the project located in the Louisiana region of MISO? | The proposed resource is required to interconnect directly to a transmission system within the Louisiana portion of MISO South, preferably within the SELPA or WOTAB region.
Is the project located within the SELPA or WOTAB region?
Is the project interconnected to the Louisiana region of MISO South Transmission system? | ELL requires that any proposed Solar PV resource interconnect directly to the Louisiana region of MISO Transmission System
Does Bidder have full control over the project site or a binding and enforceable contract to obtain full control of the project site? (Note: LOI or MOU will not constitute site control.)
If Bidder does not currently have full site control, what percentage of the project site does Bidder have control over, including part of the project site that is subject to a binding and enforceable agreement? | Bidder must show that Seller, or an Affiliate under Seller’s control, has control of 75% or more of the project site or an enforceable contract to obtain control of at least 75% of the project site for at least the full delivery term
Does Bidder have control or binding and enforceable contracts to obtain control over the gen-tie/transmission path to the point of interconnection, including through rights-of-way, easements, servitudes, etc.?
Has the Bidder provided a Phase I ESA? | Bidder must show that a recent “Phase I” or more comprehensive environmental site assessment of the project site has been performed
If Bidder has not provided a Phase I ESA, when is one expected to be available (Month, Year)
Project Financing
Has Bidder provided a plan for the financing of the project?
Has Bidder described the ownership structure of the resource?
Confirm the Bidder has reviewed and is familiar with the RFP's Appendix F - Credit-Collateral Requirements
Confirm the Bidder has provided the Form of Credit Certification | Bidder must include in the Proposal Package the completed Form of Credit Certification (Annex F-1 of Appendix F)
Confirm the Bidder accepts the credit support amounts at each milestone as outlined in Appendix F, and has factored these requirements into the proposal's pricing. | Seller will be required, without exception, to post and maintain credit support as provided in the Model Solar BOT Agreement and Appendix F
Battery Option (IF APPLICABLE)
Is an Optional Battery Included in the Proposal? | A BESS may be offered as a separately priced option for both BOT and PPA transactions.
Proposed Battery Size (MW)
Proposed Battery Duration (Hours)
Confirm the battery has minimum of four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability. | The battery energy storage system must be AC coupled with a minimum four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability.
Confirm Battery Energy Storage System is AC coupled | The battery energy storage system must be AC coupled.
Battery Equipment Manufacturer | See Scope Book Appendix 9: Approved Manufacturers
Battery Product Warranty (Years) | Minimum ten (10) years
Confirm the BESS system is solely capable of being charged by the solar panels of the project and not the power grid (i.e. BESS inverters are not capable of bidirectional charging, or disabled.)

## Solar PPA
ELL 3 GW Alternative Market-Based Mechanism Process Solar RFP - Self-Assessment for Solar PPA Proposals
Bidder ID
Resource ID
Proposal ID
Assessment Criteria | RFP Guidance | Bidder Response | Bidder Comments
Resource Overview
Delivery Term | A minimum of ten (10) consecutive years and a maximum of twenty (20) consecutive years, with an interest in fifteen (15)-year or shorter terms.
PPA Purchase Option | Bidders may propose a PPA that includes a buyer purchase option at the expiration of the Delivery Term and/or at interim milestones
Guaranteed Commercial Operation Date | The Guaranteed Commercial Operation Date may be as early as January 1, 2026.
Force Majeure Cap (Days) | The project schedule may be extended by force majeure via change order for up to a maximum total of 150 days.
MISO Interconnection Status | The proposed resource must have a fully executed GIA with MISO or be included in the 2020 or 2021 MISO DPP queue (or subsequent MISO DPP queues for which MISO has provided a Phase 1 DPP study result for the resource at the time of proposal submission ).
MISO Queue Number
Will the resource have NRIS or ERIS?
If the resource has NRIS, what NRIS amount has been requested from MISO (MW)?
If the resource has ERIS, does the Bidder anticipate electing for ELL to procure NITS in MISO at Bidder's cost and risk in lieu of Bidder obtaining NRIS? | While ELL’s strong preference is for resources that can qualify as Network Resources of ELL in MISO, ELL will not reject, and will evaluate, proposals submitted for resources that do not include the required NRIS or NITS.
Proposed Resource Size (MW) | A PPA proposal must offer at least 50 MW (AC) of Capacity.
Physical Resource Location (City and Parish)
Provide Longitude and Latitude
Provide the nearest Substation
Injection Point (POI) | The proposed resource is required to interconnect directly to a transmission system within the Louisiana portion of MISO South
Technical Feasibility
Has the Bidder provided at least two years of onsite profile data? | Bidders must provide a complete hourly generation profile of the proposed resource and explain how it was derived. The profile should be based upon verifiable data, to the extent available, for a period of two (2) or more recent years using established, reliable, and accurate data measurement equipment at or near the site of the proposed resource and/or a third-party assessment study.
What is the source of the production profile data?
Proposed Module Manufacturer | See Attachment B-1 to the Model Solar PPA (Exhibit 1: Approved Manufacturers List)
Proposed Inverter Manufacturer | See Attachment B-1 to the Model Solar PPA (Exhibit 1: Approved Manufacturers List)
Proposed Racking System Manufacturer | See Attachment B-1 to the Model Solar PPA (Exhibit 1: Approved Manufacturers List)
Please confirm that the Photovoltaic Modules in the Facility will be certified to IEC 61215 and that requirement has been factored into your bid price. | See Attachment B-1 to the Model Solar PPA
Please confirm that the Tracker system will have the functionality to move the Facility’s solar arrays to a stow or safe position in preparation for or during extreme weather events and that this requirement has been factored into your bid price. | See Attachment B-1 to the Model Solar PPA
Please confirm that the minimum height of the above-ground portion of any such foundation (measured from the top of ground level) will be greater than (i) the height required by Accepted Industry Practices based on the results of a hydrological study for the Project or Project Site conducted in accordance with Accepted Industry Practices plus an additional six inches (6”) of safety margin and (ii) twelve inches (12”) and that this requirement has been factored into your bid price. | See Attachment B-1 to the Model Solar PPA
Site Hazard Risk
Were Flood (River, Pluvial, Storm Surge) hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Flood (River, Pluvial, Storm Surge) hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Equipment elevation in terms of FEMA Flood Maps and historical water levels
Were Windstorm Hazards Identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Windstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Fastening methods used, tightening methodology, description of wind tunnel testing, etc.
Were Wildfire Hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were Wildfire hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Horizontal fire spread characteristics of the chosen panels and required setbacks for Wildfire
Were hailstorm hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were hailstorm hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Use of tempered glass panels, safe-stow position, or other ways to mitigate the risk of hail damage.
Were lightening hazards identified at the location of the site? | As determined by industry accepted natural hazard modeling software (e.g. CatNet)
If yes, were lightening hazards addressed? Provide approach to address this hazard in the Bidder's Comments section, if applicable. | Lightning protection methodology for all buildings and structures (including solar array equipment)
What is the planned designed wind speed of the facility (MPH)? | ASCE 7: Risk Category III
Bidder Experience
How many utility scale solar projects (50 MW or greater) has the bidder completed?
How many solar projects of equal or greater size to the current proposed resource has the bidder completed?
How many solar projects does the currently own and operating that are under the PPA structure?
How many solar projects does the currently own and operating that are under the PPA structure that are of equal of greater size of the current proposed resource?
Development Status
Has a detailed engineering study been performed?
Is the project cost estimate based on front-end engineering that supports at least a class 3 estimate (-20% to +30%)?
Has a detailed construction schedule (Level 1) been performed?
Is the proposal based on an EPC bid or an internal analysis?
Is Bidder (or proposed contractor) a licensed contractor, authorized to install solar equipment within the State of Louisiana?
Confirm the generation resource is located at a single facility and is not a combined or aggregate resource formed by a "system" of generation resources. | Eligible Resource are generation resources that are single resources are not and will not be part of a shared facility-type structure or arrangement
Confirm the selection of the proposed resource is not contingent on selection of another proposed resource. | Eligible Resource are single resources
Commercial
Confirm that Bidder has reviewed and is familiar with the terms of the RFP, including the Model PPA Agreement.
Has a redline of the Model PPA and the Special Exceptions tab been completed and provided?
Confirm that the Bidder will bear all risk associated with construction and arrangement for all transmission interconnection and network upgrades associated with the Facility being fully deliverable to MISO. | All proposals must provide or accept that Bidder is responsible for all costs to obtain the interconnection, deliverability, and transmission service associated with the proposal, including, without limitation, costs associated with transmission interconnection and any network upgrades for the resource.
Provide a date, which must be at or prior to the proposed PPA Start Date, by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Guaranteed Commercial Operation Date.
Does Bidder's proposal trigger, or is it expected to trigger, long-term liability recognition by ELL, including variable interest entity, derivatives, or capital lease recognition? | ELL will not accept the risk that any long-term liability will or may be recognized on its (or any of its Affiliates’) books in connection with any PPA entered into pursuant to this RFP, whether the long-term liability is due to lease accounting, the accounting for a variable interest entity or derivatives, or any other applicable accounting standard or requirement.
Confirm the Bidder has provided the Form of Accounting Certification and understands the terms outlined in the signed 2024 ELL Solar RFP Accounting Certification. | If requested by ESL, Bidder must include in the Proposal Package the completed Accounting Certification of the Agreement (Attachment E of Due Diligence)
Does Bidder agree to pay liquidated damages if the guaranteed annual energy delivery minimums are not met and Buyer's right to terminate the PPA for specified failures to meet energy delivery minimums | PPAs will include guaranteed annual energy delivery minimums entitling ELL to liquidated damages if the minimums are not met and to terminate the PPA for specified failures to meet energy delivery minimums over any two (2) consecutive contract years or any three (3) contract years (whether or not consecutive).
Does Bidder agree to absorb the risks of the possible disallowance, disapproval, or denial of recovery by the LPSC and other Governmental Authorities of ELL's costs incurred in connection with a PPA arising out of this RFP | Seller will be required to absorb the risks of the possible disallowance, disapproval, or preclusion of recovery by the LPSC and/or other Governmental Authorities of ELL costs incurred in connection with a PPA arising out of this RFP
Does the Bidder agree to financially settle a the ELL load node | Products will be financially settled at the ELL Load Node.
Site Assessment
Is the project located in the Louisiana region of MISO? | The proposed resource is required to interconnect directly to a transmission system within the Louisiana portion of MISO South, preferably within the SELPA or WOTAB region.
Is the project located within the SELPA or WOTAB region?
Is the project interconnected to the Louisiana region of MISO Transmission system? | ELL requires that any proposed Solar PV resource interconnect directly to the Louisiana region of MISO Transmission System
Does Bidder have full control over the project site or a binding and enforceable contract to obtain full control of the project site? (Note: LOI or MOU will not constitute site control.)
If Bidder does not currently have full site control, what percentage of the project site does Bidder have control over, including part of the project site that is subject to a binding and enforceable agreement? | Bidder must show that Seller, or an Affiliate under Seller’s control, has control of 75% or more of the project site or an enforceable contract to obtain control of at least 75% of the project site for at least the full delivery term
Does Bidder have control over the gen-tie/transmission path to the point of interconnection, including through rights-of-way, easements, servitudes, etc.?
Has the Bidder provided a Phase I ESA? | Bidder must show that a recent “Phase I” or more comprehensive environmental site assessment of the project site has been performed
If Bidder has not provided an ESA, when does the Bidder expect one to be available? (Month, Year)
Project Financing
Has Bidder provided a plan for the financing of the project?
Has Bidder described the ownership structure of the resource?
Confirm the Bidder has reviewed and is familiar with the RFP's Appendix F - Credit-Collateral Requirements.
Confirm the Bidder has provided the Form of Credit Certification. | Bidder must include in the Proposal Package the completed Form of Credit Certification (Annex F-1 of Appendix F)
Confirm the Bidder accepts the credit support amounts at each milestone as outlined in Appendix F, and has factored these requirements into the proposal's pricing. | Bidder will be responsible for developing and submitting proposals in this RFP that take into account (including in proposal pricing) the results of the creditworthiness evaluation and complying with the terms of Appendix F.
Battery Option (IF APPLICABLE)
Is an Optional Battery Included in the Proposal? | A BESS may be offered as a separately priced option for both BOT and PPA transactions.
Proposed Battery Size (MW)
Proposed Battery Duration (Hours)
Confirm the battery has minimum of four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability. | The battery energy storage system must be AC coupled with a minimum four-hour discharge and have 24 hours a day, 7 days a week charging and discharging capability.
Confirm Battery Energy Storage System is AC coupled. | The battery energy storage system must be AC coupled.
Battery Equipment Manufacturer | See Attachment B-1 to the Model Solar PPA (Exhibit 1: Approved Manufacturers List)
Please confirm that the Storage Facility will be certified to UL 9540, UL 1741, and IEEE 1547 by an NRTL and that requirement has been factored into your bid price. | See Attachment B-1 to the Model Solar PPA

## Special Exceptions
Section Reference | Detailed Description of the Issue | Issues Type | Proposed Alternative or Alternate Language | Issues Type Table
|  |  |  | Tier 1 | Concept Unacceptable in Any Form
|  |  |  | Tier 2 | Concept Needs Significant Modifications
|  |  |  | Tier 3 | Concept Needs Some Modification
|  |  |  | Tier 4 | Concept Needs Minor Modification
|  |  |  | Tier 5 | May be Acceptable but Requires Further Clarification

## Drop Down Lists (hidden)
|  | Fixed/Tracking | Term | C38-DEV | Typical Unit Operation Role | Proposed Panel Type | PV Module Manufacturer | Inverter Manufaturer | Racking System Manufacturer | Meteorological Towers | Wind Turbines | Transformers | Switchgear | Battery Manufacturer | Battery Storage Type | MISO Interconnection Status | SPP Interconnection Status | Guaranteed ITC percentage | Start of Construction Approach to Securing the ITC | Year in Which the Project was Safe Harbored | Physical Resource Location
Yes | PPA | Fixed | 10 | EPC | Intermittent | Monofacial Monocrystalline | Jinko | GE | Array Technologies Inc. | Nello Corporation | GE | ABB | ABB | Samsung | Confirmed (DC) | Executed GIA with MISO | Executed GIA | 30% | Physical Work Test | Before 2020 | Inside ELL Load Zone | 1 | COD
No | BOT | Tracking | 11 | Internal | Dispatchable Intermittent | Monofacial Polycrystalline | Trina | TMEIC | NexTracker | Renewable NRG Systems | Siemens | Waukesha | Cutler-Hammer | LG Chem | Not Confirmed (Other) | Review Process of Draft GIA | Pending GIA | 26% | 5% Spend Test | 2020 | Outside ELL Load Zone | 2 | Commercial Operation Date - (BOT - Guaranteed Substantial Completion)
N/A |  |  | 12 |  | Other | Monofacial Thin-Film | LG | Schneider | Game Change |  | Vestas | Siemens | GE | BYD | Battery Not included in Proposal | 2021 MISO DPP Queue | DISIS-2018-001 | 22% | Other | 2021 | Inside MISO South |  | Commercial Operation Date - (PPA - Guaranteed Commercial Operation Date)
|  |  | 13 |  |  | Bifacial Monocrystalline | Hanwha Q CELLS | Power Electronics | SunLink |  |  | Alstom | Powell | Panasonic |  | 2020 MISO DPP Queue | DISIS-2017-002 | 10% |  | 2022 | Outside MISO South
|  |  | 14 |  |  | Bifacial Polycrystalline | Canadian Solar | SMA | Shoals |  |  | Hyundai |  | Tesla |  | 2019 MISO DPP Queue | DISIS-2017-001 | Other |  | 2023 | Other
|  |  | 15 |  |  |  | FirstSolar | Chint | RBI |  |  | Virginia Transformer |  | Other | [5 empty] | 2024 |  |  | PPA | BOT
|  |  | 16 |  |  |  | Astronergy | Ingeteam | Schletter |  |  | Pennsylvania Transformer | [7 empty] | 2025 |  |  | Is the Financial Delivery Point EES.ELILD (ELL Load Node), as offered in the proposal? | Confirm that Bidder has included a "wrap" warranty with the proposed project. Indicate whether a 2 or 3 year base "wrap" warranty is included in the proposal.
|  |  | 17 |  |  |  | Talesun | ABB | TerraSmart |  |  | Cooper | [10 empty] | Confirm the Bidder is agreeing to bear the basis differential between the pricing at the Physical Delivery Point and the Financial Delivery Point (ELL Load Node). | Confirm that Bidder has offered warranties consistent wih the Design and Operating Considerations listed in Section 2.8 of the Main Body.
|  |  | 18 |  |  |  | LONGi | Sungrow | Ideematec |  |  | PACS | [10 empty] | Confirm the Bidder is agreeing to bear the Cost Recovery Risks associated with the PPA, including unrecovered costs to replace capacity and energy not provided to ELL by Seller under the applicable PPA. | Confirm that Bidder understands and agrees to accept the BOT structure, including, but not limited to, payment structure, construction risk, and transfer of ownership as set forth in the Model BOT Agreement.
|  |  | 19 |  |  |  | Phono Solar (SUMEC) | Other | Unirac |  |  | Howard | [10 empty] | Provide a date, which must be at or prior to the proposed Guaranteed Commercial Operation Date, by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Guaranteed Commercial Operation Date (PPA proposals). | Provide a date, which must be at or prior to the proposed Guaranteed Substantial Completion Date), by which Bidder would require all network upgrades to be completed in order to successfully achieve the project’s proposed Guaranteed Substantial Completion Date (BOT proposals).
|  |  | 20 |  |  |  | Yingli |  | SunPower
[7 empty] | JA Solar |  | Soltec
[7 empty] | Suntech |  | Nclave
[7 empty] | Maxeon (SunPower) |  | Other
REC Solar
Risen
HT Solar
Seraphin
Other